**R: 2018-134**

**A RESOLUTION OF THE**

**TOWN OF PHILLIPSBURG, COUNTY OF WARREN,**

**STATE OF NEW JERSEY, AMENDING RESOLUTION NO. 2018-106**

**WHEREAS,** the Town of Phillipsburg previously adopted Resolution No. 2018-106 approving a change order request for a decrease in the amount of $19,297.82 from an original award of $91,754.80 for work associated with Samson Concrete & Masonry for the replacement of pedestrian crosswalks (the “Project”); and

**WHEREAS**, Resolution 2018-106 failed to account for a change order in the increased amount of $8,268.68, which increased the total contract price to $100,023.48; and

**WHEREAS,** the total contract price of $100,023.48 less the deduction of $19,297.82 results in a final contract price of $80,725.66.

**NOW THEREFORE IT BE RESOLVED** by the Town Council of the Town of Phillipsburg, County of Warren, State of New Jersey, that Resolution No. 2018-106 shall be amended to change the final contract price for the Project to $80,725.66 for the reasons stated above.

**CERTIFICATION**

I, Victoria L. Kleiner, Municipal Clerk for the Town of Phillipsburg, do hereby certify that the foregoing is a true copy of a resolution duly adopted by the Town Council at their July 17, 2018 meeting.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Victoria L. Kleiner, Municipal Clerk